## Test Plan
TEST PLAN
Project ID:
| PROJECT NAME: | SSN |  | P kumaraswamy
| SRS | SSN |  | 2023-07-03
|  |  |  | 2 | Soni Sharma/ P Kumaraswamy
| Date: | 2023-07-03 |  | P Kumaraswamy
I | Scope
1 | Smoke, Functional, Compatability & Regression Testing.
2 | Scope of the testing activity is entirely in QA environment.
3 | Application should function properly in all the URL's.
4 | Responsive Testing in Android device
II | Main Module | Functions/ Features to be tested |  | Below check are required | Testing Mode
1 | Your Brand Cover | 1. UI/ UX Improvements (Mobile and Desktop) + YBC Revamp(Testing) 2. OTP verification page for new user- when I clicked entered a wrong number, I am not able to move to otp page after entering a new number. 3.Phone number validations- follow the rules that are for EO |  | add /edit/ delete appliances UI/UX in Responsive mode and Mobile Simmulator mode. End- to- End Flow of the Appliation. | Manual
2 | Encash Offers crm_Admin | 1.EN-613 Admin panel for input of Meta data |  |  | Manual
3 | EncashOffers UI | 1. User Count¦ EO¦ Today No of landing value is showing different -2 in M-Fuel and EO link 2.EN-612 SEO related updates in URL for EO |  |  | Manual
4 | MFuel | 1. Mfuel - Date, Time, IPAddress will be added in the all listing page 2. Table filters and sorting feature |  |  | Manual
III | Functions/ Features not to be tested
IV | Assumptions & Constraints
1 | Build is available on time.
2 | Build is stable enough to be tested(All Smoke test scenarios are passed and they work consistently).
3 | New changes in any form(s) are avoided which are not planned.
4 | Requirement documents are clear and available for testing team.
5 | Availability and Access to necessary Testing tools for the Testing team.
6 | Dedicated Test Environment for Testing - Should be identical to Production.
7 | Resources are available.
V | Test Strategy
1 | Build deployment on respected URL.
2 | Carrying out Smoke test.
3 | Testing all the Implemented requirements on Multiple supported browsers.
4 | Reporting Defects in Jira.
5 | Retesting the Implemented defects.
6 | Carrying out Regression testing (based on the Regression List).
7 | Publishing Report(s).
VI | Testing Methodology
| Testing Type |  |  | In Scope
1 | Smoke Testing |  |  | Yes
2 | Functional Testing |  |  | Yes
3 | Regression Testing |  |  | Yes
4 | Compatability Testing |  |  | Yes
5 | User Acceptance Testing |  |  | Yes
VII | Test Approach
| Testing Type | Test Objective |  | Environment | Exit Criteria
1 | Documentation | Produce documents for Testing purpose. |  | Local | TestCase, User manual ,RTM, HTML Reports etc..
2 | Smoke/ Build verification | To carry out Smoke test as soon as the build is deployed. |  | Local | All the test cases should PASS.
3 | Integration Testing | To test Integration of modules/sub-modules. |  | Local | All the test cases/scenarios should PASS.
4 | Compatibility | Testing across the supported OS versions and browsers. |  | Local | The application should behave consistently across various supported platforms.
5 | User Interface | Look & Feel of the application based on the User requirement. |  | Local | Depending on the requirement.
IX | Test Schedule
| Releases | From Date (DD-MM-YYYY) | To Date (DD-MM-YYYY) | Activity
1 | Release 0.2/ Sprint 2 | 2023-06-22 | 2023-06-24 | Preparing Test Plan for Second Sprint.
|  | 2022-06-25 | 2022-06-27 | Preparing Test cases.
|  | 2023-06-28 | 2023-06-29 | Smoke testing starts on Web build
Functional Testing, i.e. Executing Test Cases & Reporting bugs.
|  | 2023-06-30 | 2023-06-30 | Functional Testing, i.e. Executing Test Cases & Reporting bugs.
|  | 2023-07-01 | 2023-07-01 | Re-Testing for Fixed bugs.
|  | 2023-07-02 | 2023-07-02 | Regression Testing.
|  | 2023-07-03 | 2023-07-03 | Test Summary Report Publication
X | Test Phase
| Level | Test cases |  | Test Data Prepared By | Completion Criteria
Written By
|  | Tushar |  |  | Functionality Working fine as per Requirement
1 | Smoke | Soni Sharma & Kumaraswamy |  | P kumaraswamy
2 | Integration | Soni Sharma & Kumaraswamy |  | P kumaraswamy
3 | Functional | Soni Sharma & Kumaraswamy |  | P kumaraswamy
4 | Compatibility | Soni Sharma & Kumaraswamy |  | P kumaraswamy
5 | Functional Testing | Soni Sharma & Kumaraswamy |  | P kumaraswamy
XI | Resources
1 | Tester |  | Soni Sharma & Kumaraswamy
2 | Software Requirements |  | OS, Browsers, Mobile Simulator Plugin.
3 | Tools |  | Jira / WPS office
XII | Suspension and Resumption Criteria
1 | When a defect is introduced that cannot allow any further testing.
2 | Temporarily suspending the testing process - Build contains many serious defects which seriously prevent or limit Testing Process.
3 | Unavailability of external dependent systems during execution.
4 | Resuming Testing process the problem(s) that caused the suspension have been resolved.
XII | Risk Analysis
1 | Lack of personnel resources and hardware/software resources.
2 | Complex/Sudden requirement changes.
3 | Wrong budget estimation.
4 | Major Issue which cant be resolved quickly.
XIII | application also need to be tested on below mention Browsers
| Browsername |  |  | Below checks are Required | Testing Mode
1 | Firefox |  |  | 1) The condition of apperiance of the page in different browser- is it the same, is it different, if one is better then the others , etc 2) The Functionality and the working on it | Manual
2 | Edge |  |  |  | Manual
3 | Chrome |  |  |  | Manual
4 | mobile Responsive |  |  |  | Manual
5 | Andriod Devices |  |  |  | Manual