## Test Plan
TEST PLAN
| Project ID: |  | URL: | schedassist.com
| PROJECT NAME: | SSN | Prepared BY: | P kumaraswamy
| SRS | SSN | Last Updated Date: | 2022-05-02
|  |  | No fo Resource: | 2 | Soni Sharma/ P Kumaraswamy
| Date: | 2022-02-23 | Review BY: P kumaraswamy | P kumaraswamy
https://app.asana.com/0/1203522460633188/1203522460633205/f
I | Scope
1 | Smoke, Functional, Compatability & Regression Testing.
2 | Scope of the testing activity is entirely in QA environment.
3 | Application should function properly in all the URL's.
4 | Responsive Testing in Android & ios device
II | Functions/ Features to be tested |  | Below check are required |  | Testing Mode
1 | Super admin Dashboard | 1. Signup /Signin /OTP 2. OTP by Email confirmation 3. Reset Password |  |  | Manual/Automation
2 | Business | 1. Services 2. Clinics 3. Members 4. Insurance | add /edit/ delete services add/edit/delete/assign clinic/select doctor/select admin add/edit/delete / suspend members/member limits if using trial plan Insurance /filter |  | Manual/Automation
3 | ADMINISTRATOR | 1. Account setting 2. Web Settings 3. Billing & payments | Default admin/ default doctor Delete account new subscription/ downgrade / upgrade / payment |  | Manual/Automation
4 | Domain Settings | 1. Domain.change 2. Sub Domain Change |  |  | Manual/Automation
5 | Chat Bot | 1. Create Bot 2. Delete Bot 3. Enable Bot 4. Disable bot |  |  | Manual/Automation
6 | Others | 1. Support 2. Video Tutorial 3. Site Map | Client will provide the details for future implement |  | Manual/Automation
7 | Theam Change |  |  |  | Manual/Automation
8 | Notifications | Desktop Notification Browser Notification | Browser notification / Email noitification |  | Manual/Automation
III | Functions/ Features not to be tested
1 | Members Delete
2 | Patient Data Export Functionality.
3 | File Upload Functionality.
4 | Domain change
5 | Chat Boat in Super Admin
6 | Theam Change
7 | Notification in Macbook
IV | Assumptions & Constraints
1 | Build is available on time.
2 | Build is stable enough to be tested(All Smoke test scenarios are passed and they work consistently).
3 | New changes in any form(s) are avoided which are not planned.
4 | Requirement documents are clear and available for testing team.
5 | Availability and Access to necessary Testing tools for the Testing team.
6 | Dedicated Test Environment for Testing - Should be identical to Production.
7 | Resources are available.
V | Test Strategy
1 | Build deployment on respected URL.
2 | Carrying out Smoke test.
3 | Testing all the Implemented requirements on Multiple supported browsers.
4 | Reporting Defects in Bug Net.
5 | Retesting the Implemented defects.
6 | Carrying out Regression testing (based on the Regression List).
7 | Publishing Report(s).
VI | Testing Types
| Testing Type |  |  | In Scope
1 | Smoke Testing |  |  | Yes
2 | Functional Testing |  |  | Yes
3 | Regression Testing |  |  | Yes
4 | Compatability Testing |  |  | Yes
5 | User Acceptance Testing |  |  | Yes
VII | Test Approach
| Testing Type | Test Objective | Entry Criteria Activity | Environment | Exit Criteria
1 | Documentation | Produce documents for Testing purpose. | Preparing Testing Documents - Testcases, User Manual, RTM etc. | Local | TestCase, User manual , HTML Reports etc..
2 | Smoke/ Build verification | To carry out Smoke test as soon as the build is deployed. | The existing Smoke test cases suite will be used for this. | Local | All the test cases should PASS.
3 | Integration Testing | To test Integration of modules/sub-modules. | The existing and newly implemented features should work as expected. | Local | All the test cases/scenarios should PASS.
4 | Compatibility | Testing across the supported OS versions and browsers. | Executing Compatibility test cases across various supported platforms. | Local | The application should behave consistently across various supported platforms.
5 | Security | To carry out Security testing on the application | Executing Security test cases - Session & Cookie Testing. | Local
6 | User Interface | Look & Feel of the application based on the User requirement. | UI Testing based on the provided screenshots. | Local | Depending on the requirement.
7 | Data and Database Integrity Testing | Covered while doing the above tests. |  | Local
8 | User Acceptance | Implementing in clients place. | Implementing and performing testing the application in clients place. | UAT (Same as Production) | Acceptance by the Client.
VIII | Defect Classification
| Severity | Severity Code | Weightage | Defect Description
1 | Critical | S1 | 10 | Defect that would result in failure of the software element with no possible workaround. A showstopper defect.
2 | Major | S2 | 5 | Defect that would result in failure of the software element but has a possible workaround.
3 | Minor | S3 | 1 | Defect that would affect only the non-functional aspects of the software elements.
4 | Recommendation | S4 | 8 | This is not a typical defect but a viewpoint that the reviewer wants to recommend. Corrective action may or may not be taken against this.
IX | Test Schedule
| Releases | From Date (DD-MM-YYYY) | To Date (DD-MM-YYYY) | Activity
1 | Release 0.2/ Sprint 2 | 2022-04-25 | 2022-04-26 | Preparing Test Plan for Second Sprint.
|  | 2022-04-26 | 2022-05-03 | Preparing Test cases.
|  | 2022-05-26 | 2022-05-27 | Smoke testing starts on Web build
Smoke Testing Report is sent.
|  | 2022-06-06 | 2022-06-10 | Functional Testing, i.e. Executing Test Cases & Reporting bugs.
|  | 2022-06-21 | 2022-06-24 | Re-Testing for Fixed bugs.
|  | 2022-06-27 | 2022-06-28 | Regression Testing.
|  | 2022-06-29 | 2022-07-01 | Test Summary Report Publication
X | Test Phase
| Level | Test cases |  | Test Data Prepared By | Completion Criteria
|  | Written By | Based On
1 | Unit Testing | Tushar | SRS
2 | Smoke | Soni Sharma & Kumaraswamy |  | P kumaraswamy
3 | Integration | Soni Sharma & Kumaraswamy
4 | Functional | Soni Sharma & Kumaraswamy | Use Cases | P kumaraswamy
5 | Compatibility | Soni Sharma & Kumaraswamy | SRS and Business Scenarios | P kumaraswamy
7 | Functional Testing | Soni Sharma & Kumaraswamy |  | P kumaraswamy
8 | Non-Functional Testing
XI | Resources
1 | Tester |  | Soni Sharma & Kumaraswamy
2 | Software Requirements |  | OS, Browsers, Mobile Simulator Plugin.
3 | Tools |  | Jira / Selenium / Testng / Java / Eclipse/WPS office
XII | Suspension and Resumption Criteria
1 | When a defect is introduced that cannot allow any further testing.
2 | Temporarily suspending the testing process - Build contains many serious defects which seriously prevent or limit Testing Process.
3 | Unavailability of external dependent systems during execution.
4 | Resuming Testing process the problem(s) that caused the suspension have been resolved.
XII | Risk Analysis
1 | Lack of personnel resources and hardware/software resources.
2 | Complex/Sudden requirement changes.
3 | Wrong budget estimation.
4 | Major Issue which cant be resolved quickly.
XIII | application also need to be tested on below mention Browsers
| Browsername |  | Application is by suporting Browser | Below checks are Required | Testing Mode
1 | Firefox |  | YES | 1) The condition of apperiance of the page in different browser- is it the same, is it different, if one is better then the others , etc 2) The Functionality and the working on it | Manual
2 | Edge |  | YES |  | Manual
3 | Chrome |  | YES |  | Automation
4 | mobile Responsive |  | YES |  | Manual
5 | Andriod Devices |  | No |  | Manual